## Sheet1
Page | Date | Bug
loadnsave | 2015-01-02 | When a locale is saved there is no control of where it is saved or what the file is called | no idea how to do this
Page | Date | Queries
loadnsave | 2014-12-22 | It would be enormously helpful if, when you've loaded a locale, the locale name was displayed as a header on every page | Sort of done. Perfect!
| 2015-01-22 | This works perfectly for loading from, and saving to, a local file; it doesn't work when fetching a file from the SLDR. Ideally it should also be updated when someone changes the language id or script id and clicks on the <Save> button. That way it will always show the id of the locale you're going to save.
loadnsave | 2015-01-02 | ldmledit appears to strip out all line breaks, so a locale which looks OK when viewed with eg Notepad before editing, has lost all its formatting after editing. Using a specialist xml editor, however, the data still looks OK. | it outputs linebreaks only, not carriage return linebreak. Please use an appropriate editor. That's sort-of OK except that currently all SLDR locales do have carriage return linebreaks, so ldmledited locales are different from all the others. That isn't ideal.
identity | 2014-12-22 | I'm conscious that in CLDR locales the Script ID is usually not entered (instead being derived from the language entry in the likelySubtags table). If we encourage users always to enter the script, so it's explicit, is there a danger we could end up with 2 IDs for the same locale (eg CLDR: nnh.xml, SLDR: nnh_Latn.xml)? I'm not sure what the best solution is
identity | 2015-01-22 | There is a similar issue with languages which have both a 2-character ISO code (eg te) and a 3-character code (eg tel). Potentially we could end up with two different files for the same locale. I'm wondering whether we should 'normalise' the locale id (eg by referencing likely subtags), so if someone keys in language: tel and script: Latn, it will be normalised from tel_Latn to te.
| 2015-01-21 | ANRCC request: It would be nice if the language and script codes could be selected from drop-down boxes, instead of being free text.
loadnsave | 2015-01-21 | Page links tidied up and pushed: s.s.o. needs updating
identity | 2015-01-22 | Prompts changed: changes need committing
all | 2015-01-22 | ANRCC request: it would be better if links to ldml spec pages opened in a new window. (I chgd thehtml, but it didn't seem to help.)
dates | 2015-01-22 | ANRCC request: Make simpler dates page, with just a few prompts
loadnsave | 2015-01-22 | It would be valuable if a parent locale could be specified on the loadnsave page (eg Telugu for Gondi)

## 21Jan15_archive
Page | Date | Bug
loadnsave | 2015-01-02 | When a locale is saved there is no control of where it is saved or what the file is called | no idea how to do this
misc | 2014-12-22 | Details entered (eg Line Direction) aren't saved. Applies to both new and existing locales | fixed as part of later bug
| 2015-01-06 | This still isn't working for me, for either new or existing locales. If I enter Line Direction I'm expecting the following to be generated: <layout> <orientation> <characterOrder>right-to-left</characterOrder> </orientation> </layout>
| 2015-01-09 | Line Direction and Yes/No info is now being saved, but it isn't displayed when the locale is loaded
misc | 2014-12-22 | There is no way to enter List Patterns. A "+" button below the No string box doesn't do anything | fixed
| 2015-01-06 | For an existing locale list patterns are now displayed, but the type parameter is missing (eg <listPattern type="unit"> or <listPattern type="unit-short">); the listPatternPart type is the one that's displayed. For new locales I can't enter anything. That said, we won't be entering list patterns at ANRCC anyway so it's a low priority to fix.
misc | 2014-12-22 | There are no <Save> and <Cancel> buttons on this page | fixed
| 2015-01-06 | I'm still not seeing these buttons: are there changes which haven't been pushed to s.s.o.?
misc | 2015-01-09 | Most of the above looks to be working now - thanks!
resources | 2014-12-22 | Resource details can be added, but there are no <Save> or <Cancel> buttons on the page | they appear when you edit a particular entry (click the edit icon) OK
resources | 2014-12-22 | Generated ldml wrong for spell-checking (superfluous <sil:url/>) | that comes from entering an empty new spell checker and not filling in the details OK
resources | 2015-01-02 | When clicking on the Edit symbol to add a Spell Checker, the two fields prompted for are labelled "Type" and "Type": should the labels be "Name" and "URL"? | fixed OK
Page | Date | Queries
loadnsave | 2014-12-22 | It would be enormously helpful if, when you've loaded a locale, the locale name was displayed as a header on every page | Sort of done. Perfect!
loadnsave | 2015-01-02 | ldmledit appears to strip out all line breaks, so a locale which looks OK when viewed with eg Notepad before editing, has lost all its formatting after editing. Using a specialist xml editor, however, the data still looks OK. | it outputs linebreaks only, not carriage return linebreak. Please use an appropriate editor. That's sort-of OK except that currently all SLDR locales do have carriage return linebreaks, so ldmledited locales are different from all the others. That isn't ideal.
identity | 2014-12-22 | I'm conscious that in CLDR locales the Script ID is usually not entered (instead being derived from the language entry in the likelySubtags table). If we encourage users always to enter the script, so it's explicit, is there a danger we could end up with 2 IDs for the same locale (eg CLDR: nnh.xml, SLDR: nnh_Latn.xml)? I'm not sure what the best solution is
| 2015-01-06 | NB: I've added help text to the loadnsave page
| 2015-01-09 | New help text still isn't showing up
| 2015-01-09 | I've now also added help text to the misc page